MAKEREADY BY G54 — PRICE QUOTATION

Phased Program Proposal

Funded roadmap of fixed-fee phases — SAP B1 / Sage 100 replacement

| Client | Great Mountain West (g54.com) |
| --- | --- |
| Prepared By | Christopher Wall |
| Provider Email | ck.wall@icloud.com |
| Product | MakeReady — Print MIS / ERP Platform |
| Date | July 25, 2026 |
| Status | Draft for client review |
| Net after Discovery credit | $195,000 |
| With Foundation prepay | $193,000 net |

| Program Total (Phases 1-8) | $200,000 |
| --- | --- |

1.  Engagement Model

MakeReady is delivered as a funded roadmap of fixed-fee phases against a fixed program budget of $200,000 (Phases 1-8). Each phase produces working, deployable software and is independently useful; Great Mountain West funds one phase at a time, and the per-phase fees below sum to the $200,000 cap. Each phase fee is a fixed allocation of that budget, confirmed against the phase's requirements at kickoff.

Note on depth: the full 8-phase scope at SAP Business One parity is independently estimated at $335,000-$495,000 to build to depth, and materially more at agency market rates (see the companion market benchmark). Delivering it within the $200,000 cap prioritizes core functionality per phase and defers lower-value depth to later change requests.

2.  Phase 0 — Discovery & Design (complete)

| Item | Detail |
| --- | --- |
| Fee | $5,000 flat — due at project start |
| Deliverables | Full handoff package: 17 prototype screens, per-module requirements, data model, architecture |
| Credit | Credited in full against Phase 1 on award of the Foundation build |

3.  Build Phases & Pricing

| Phase | Scope | Fixed Fee |
| --- | --- | --- |
| Phase 1 | Platform Foundation + Customer & Sales | $71,000 |
| Phase 3 | Web Store (Native B2B) — conditional | $23,000 |
| Phase 4 | Operations | $23,000 |
| Phase 5 | Finance & Accounting (+ legacy data migration) | $36,000 |
| Phase 6 | Content Library (DAM) | $20,000 |
| Phase 7 | Field Sales RBAC & Mobile | $11,000 |
| Phase 8 | Workflows, Reports & Intelligence | $16,000 |
|  | Program Total (Phases 1-8) | $200,000 |

Phase 1 bundles Platform Foundation ($50,000) and Customer & Sales ($21,000). Prepay incentive: pay the $50,000 Foundation fee in full in advance and the Customer & Sales work is discounted from $21,000 to $19,000 — a $2,000 saving, making the Phase 1 bundle $69,000.

4.  Discounts & Net Total

| Line | Amount |
| --- | --- |
| Program list total (Phases 1-8) | $200,000 |
| Less: Discovery fee credited against Phase 1 | - $5,000 |
| Net program total | $195,000 |
| Optional: Foundation prepay incentive | - $2,000 |
| Net with Foundation prepay | $193,000 |

5.  Phase Scope Detail

Phase 1

Platform Foundation + Customer & Sales (bundled): auth, RBAC (6 roles), user mgmt, system config, role dashboards, audit log, notifications, full platform infrastructure (single-tenant, design system, CI/CD, encryption, secure SDLC) + security-documentation deliverable; Business-Partner master, account groups, contacts, activity log, quotes/estimates, sales orders, delivery, AR invoice, incoming payment (quote-to-cash).

Phase 3

Web Store (Native B2B): storefront, catalog, account-group pricing, order management, Web→Sales-Order automation, approval rules, status sync. (Conditional — replaced by a smaller integration scope if the existing eCommerce platform is retained.)

Phase 4

Operations: job creation from Sales Order, production queue, status tracking, artwork attachment, item master, stock, inventory publishing, Quality Management, Equipment Maintenance.

Phase 5

Finance & Accounting: chart of accounts, AR, AP, bank reconciliation, journal entries, tax, cost centers, budgets, P&L by segment, fixed assets, depreciation, and complete legacy-ERP data migration (legacy system decommissioned).

Phase 6

Content Library (Digital Asset Management): asset upload, LLM-powered auto-tagging & descriptions, natural-language + visual-similarity search, collections, usage rights/history, job linking, thumbnails.

Phase 7

Field Sales RBAC & Mobile: field-sales role dashboards, mobile-responsive order upload, client artwork upload, sales-manager oversight.

Phase 8

Workflows, Reports & Intelligence: approval rules engine, sales/production/financial dashboards, asset reports, CSV/PDF export.

6.  Payment Terms

Phase 0 (Discovery): $5,000 due at project start; credited against Phase 1 on award of the Foundation build.

Build phases: 50% at phase kickoff, 50% at phase acceptance. Phase 1's kickoff invoice is reduced by the $5,000 Discovery credit.

Foundation prepay incentive: pay the $50,000 Foundation fee in full in advance and Customer & Sales is discounted from $21,000 to $19,000 (a $2,000 saving).

Phases are funded one at a time; Great Mountain West is not obligated beyond a confirmed phase. The $200,000 program cap is fixed.

Phase 3 (Web Store) is conditional — if the existing eCommerce platform is retained and integrated instead, this phase is dropped and a smaller integration scope is quoted separately.

Out-of-scope change requests are quoted separately before work begins and fall outside the $200,000 budget.

Third-party costs (hosting, LLM API usage, payment processing, domain/SSL) billed at cost.

7.  Basis of Estimate

This is a good-faith forecast estimate based on the current requirements, wireframes, and data model. Each phase fee firms up at kickoff against that phase's finalized requirements; the $200,000 figure is a fixed program cap, not a guaranteed total for full SAP B1 parity (estimated separately at $335,000-$495,000 to build to depth). Material scope changes are documented in writing and priced before the affected work begins.

| Great Mountain West Signature: ___________________________ Printed Name: ___________________________ Date: ___________________________ | Christopher Wall Christopher Wall Principal Developer Signature: ___________________________ Printed Name: ___________________________ Date: ___________________________ |
| --- | --- |

This quotation is confidential and intended solely for the use of Great Mountain West and Christopher Wall. Unauthorized distribution is prohibited.